# Project Handoff: Next Steps

## Population Data

### Acquire population from Ethnologue

There are a few ways to approach this. One option is to purchase a custom global dataset from Ethnologue that includes speaker populations (L1, L2, and counts that are neither L1 or L2), the source of each population estimate, and the year the estimate was recorded. Another option, potentially, is to partner with a university on this project, to see if they could provide both the Ethnologue data we need and additional subject-matter expertise.

### Normalize the data to a common year

Once you have the data, normalize all entries to show approximated figures for the same year. Use the population estimate scaling method from “Double Jeopardy and Climate Impact in the Use of Language Models: Socio-economic Disparities and Reduced Utility for Non-English Speakers” (Solatario, Stefanini, Krambeck, and Dupriez; arXiv:2410.10665).  This is the method project team has agreed on, but if future researchers determine another method is better feel free to update it.

### Verify comparability across sources

Once you have the data, review its sources to understand whether population estimates are actually comparable across them. Population estimates come from independent studies, country-sponsored census data, UN-sponsored census data, and more – each with different collection years and likely different sampling methodologies. This matters because many low-resource languages are spoken in countries where censuses may not have been conducted in 20+ years, or methodology hasn’t been validated, so it’s important to understand how reliable the underlying population data actually is before relying on it.

## Tier A – Hugging Face Harvest

### Resolve the parquet size-extraction validity issue

We are currently working with a three-tier size-resolution strategy. Tier 1 resolves exact counts via Hugging Face’s Datasets Server /size endpoint to get size information from configuration metadata. Tier 2 resolves counts for datasets without a per-language configuration via a column-pruned query against auto-converted parquet files, and Tier 3 flags datasets that resolve through neither for manual review. We are still running into a validity issue with the parquet size-extraction step, since Hugging Face only auto-converts the first 5GB of a dataset, and datasets on the Hub range up to hundreds of GB and multiple terabytes. The next step is to research Hugging Face’s auto-conversion algorithm more thoroughly and determine whether this three-tier approach can be salvaged, and if not, develop a new Tier A methodology that still captures everything we need (size, provenance, modality, license, etc.).

## Tier B – Language Data Trusts Harvest

### Populate the repository as trusts are developed

As language data trusts form with DDP-partner countries, add their data to the repository on GitHub and update the methodology documents to reflect the sources included in each trust, along with text/audio size estimates and any other relevant information to the index.

## Tier C – Common Crawl Harvest

### Re-run harvest on each new crawl release

This harvest and its methodology are complete. The only remaining step is to re-run the pipeline whenever Common Crawl releases new crawl data, so the repository stays on the most current version.

## Audio Harvest

### Extract audio data from Hugging Face

This step should be handled within the Tier A Hugging Face harvest itself, not as a separate step. It’s called out here only to make sure future researchers understand that the Tier A harvest extracts both text and audio data from Hugging Face.

### Resolve the Lingua Libre harvest 503 and missing source_type issues

As detailed in the challenges document, the Lingua Libre harvest is hitting two main issues. First, it returns 503 server-side errors when attempting to extract the French-language entries specifically (430k entries – the largest in the corpus, well above the next-largest language at ~200k), most likely because there is simply too much data to export from that language in a single pass. Second, source_type is coming back blank for every entry, despite the script correctly checking for a matching Commons list page via the fileusage field – it’s unclear whether this means the source truly isn’t recorded for these entries, or whether it is stored under a different field the script isn’t checking. The next step is to understand why both issues are occurring, update the harvest to resolve them, and re-run it.

### Incorporate additional audio sources

Living Tongues: Living Tongues Institute for Endangered Languages is a nonprofit that documents and helps revitalize endangered languages worldwide, and its Living Dictionaries platform lets language communities themselves build and maintain free, multimedia dictionaries – including audio recordings from named speakers – making it a directly relevant, community-sourced audio data source for exactly the kind of low-resource languages this project is trying to serve. This is a high-quality source specifically because every entry is uploaded by a speaker of that language and maintained by the language community it represents. Living Tongues does not currently have an API. After emailing their support team, they provided a spreadsheet that contains the language x transcribed audio hours (all hours are transcribed). Because there is no API, updating this data would require re-emailing and re-processing a local file every time, which is not ideal and worth factoring in when deciding whether/how to incorporate this source.

Masakhane, JW300, PanLex, Global Voices Lingua, Wikitongues, Bloom Library, & Universal Dependencies: are all worth adding into this dataset for their scope and language coverage. All of these are hosted on Hugging Face, so they should be picked up in the Hugging Face harvest.

Others: Additional candidate sources have been identified for further research and potential inclusion. They are listed on this spreadsheet.

**Note: many audio sources hosted outside of Hugging Face do not have an API. Since downloading and sizing files locally isn’t a scalable approach, it is important to determine whether these sources can be incorporated in some other way before committing to include them.

## Data Threshold Gates

### Define data threshold gates needed for each model tier

Goal: Define three data thresholds (“gates”) -- Simple, Domain-Specific, and Frontier-Grade – indicating how much text and audio data is needed to train each tier of model, for text and audio separately. These gates power the index’s headline statistic: licensed data (Tiers A + B)  / gate threshold, capped at 100%, computed per gate and per modality for peach language.

Next steps:

- Validate three provisional gate ranges below against existing literature (fine tuning studies, Whisper/XLS-R/MMS, scaling laws) and practitioner results.

- Pick one point value per gate, not just a range, to compute progress against. The point value is a presentation convention, not a scientific claim. The original range should have an uncertainty band that can be shown alongside it.

- Write a methods note documenting: the chosen gate values with citations and uncertainty bands; the caveat that audio gates are transcribed-hours only

Gate definitions:

- Simple: fine-tune existing multilingual models – classification, basic chat, basic ASR

- Domain-specific: health, agriculture, education assistants, reliable ASR

- Frontier-grade: performance comparable to high-resource languages, via cross-lingual transfer

## Build Final Index

### Code the final pipeline scripts and aggregation logic

Build scripts that aggregate all text data together and tokenize it, and separately aggregate all audio data together. Then build the scripts that actually run the harvests and build index. Ideally, a single command should refresh the index end to end by running the complete harvest, but as a back up for debugging purposes it should also be possible to re-run each harvest tier individually.

Once this is done, create a visualization of the index following this example for text data:

### 2. Build a section that helps users interpret the index

Combine population data, gate-threshold progress, general data availability, and World Bank Development Indicators (WDI) data on countries’ digital and economic readiness, to generate statements that help interpret the index and guide decisions about where to invest resources -- in data generation, model development, or both, and if the latter, what type of model.

We want the index to be able to answer questions like:

- How close in language X to being AI-ready?

- Where should future investment be directed?

For example, an insight the index should be able to generate might read: “A large portion of language X’s speakers live in countries with decent broadband access and mobile phone ownership but low literacy rates – suggesting that voice-based and SMS-based tools should be prioritized over text based ones”.

WDI data covers major social, economic, and demographic time series dating back to 1960. The one caveat: WDI is reported at the country level, so using it here requires having speaker population estimates at the country level as well, reinforcing why the population data work above is a prerequisite for this step, not a parallel, independent task.