Global Language Data Availability Index

Summer Intern Work Plan — 7 weeks

Objective. Build a reproducible, automatically updatable dataset that measures, for every major language, how much non-synthetic, clearly licensed text and audio exists for training generative AI models — and how close each language is to the data thresholds that real applications require. The index will track global progress on closing the language data gap, including the contribution of national language data trusts that aggregate copyrighted content for licensed, IP-preserving use in AI training.

The product. Each language is a bar on a log-scale data axis. Three fixed gates (which can be ranges) mark what's needed for simple, domain-specific, and frontier-grade applications. Licensed data (green) and web-available data (gray) are two layers; the gap between them is the trust opportunity. The headline statistic is gate progress = available licensed data ÷ gate threshold, capped at 100% — "Chichewa has 10% of the licensed text needed for simple applications."

# Key design decisions (confirm in Week 1; flag disagreements rather than re-deriving)

1. Languages and Countries. Data exists per language (there is a Chichewa corpus, not a "Malawi corpus"). Measure availability and gate progress per language; derive country views using Ethnologue speaker weights: (a) population-weighted average gate progress, and (b) share of population whose language has fully cleared each gate. Count first (L1) languages only in v1.0 — Ethnologue's L2 counts are soft, and the L1+L2 secondary view is deferred to v0.2 (state this in the methods). Note that country scores are not independent — a shared language (Swahili, Hausa) lifts every country where it's spoken.

Plan on collecting language data for all languages in Ethnologue dataset.

Plan on v1 only including L1 population estimates for now because it will be methodologically cleaner, but verify this once we have all the language data. Ife will spend more time thinking about whether it is possible to to combine L1 & L2 counts in a valid way.

Normalize the estimate year. (see Double Jeopardy Paper for methodology)

2. Language scope. The index focuses manual effort on trust-viable languages (enough media and government content for the trust model to operate) and says so openly in the methods.

- Curated set (~200–250 languages, full manual treatment): any of (a) ≥5M L1 speakers globally (~100–150 languages — captures every serious media ecosystem, including "minority everywhere" languages like Yoruba and Igbo); (b) the largest L1 language of any country not otherwise covered (~50–70 more — keeps every country scoreable: Icelandic, Estonian, Fijian, Dzongkha); (c) ≥25% of any country's population (edge cases only at a 5M floor); plus any language targeted by a data trust, regardless of size (Yao, Tumbuka). Confirm the exact list against Ethnologue in Week 2. Curation work must be scripted with manual review, not done language by language.

- Automated set (everything else the pipeline sees): same scripts, flagged "unvalidated," no manual effort. This is the answer to "why does the index ignore small languages" — it doesn't; it just concentrates verification where the trust model can act.

5M speaker cutoff:

- Using this because 5M speakers means its highly likely there will be media and government ecoystem for a population that big

Consider also including the diversity of data we are able to gather as a threshold as well --> there are languages that have a lot of speakers but very little data and vice versa

Trust languages threshold:

- Work with Ife and Towera to define this critera of what it means to be trust-viable

3. Text in tokens. Use one fixed, disclosed multilingual tokenizer (e.g., the Gemma tokenizer) for all languages and all time periods — tokenizer fertility varies by language, so changing it breaks the index. Report UTF-8 bytes and word counts as robustness columns. Not pages (not comparable across scripts), not raw bytes (overweight dense scripts).

Metadata: record the original recorded unit for transparency and also report normalized token estimate

4. Audio in hours, two parallel categories, never summed. Transcribed hours (what supervised ASR/TTS needs) and untranscribed hours (what self-supervised pretraining needs — wav2vec 2.0, MMS, USM). Untranscribed audio counts only from cataloged sources with published hour counts; do not estimate the universe of web audio (spoken language ID is least reliable exactly where it matters). The categories interact — abundant untranscribed audio substitutes for transcribed hours in pretraining — but v1.0 treats this as a documented caveat, not a computed adjustment: audio gates are transcribed-hours only (see Week 5).

5. Three licensing tiers, reported separately.

- Tier A — Openly licensed: explicit open licenses (CC-BY, CC0, Apache) on Hugging Face, OpenSLR, Common Voice, GitHub. Usable by anyone.

- Tier B — Rights-cleared for training: copyrighted data under negotiated training licenses — the output of data trusts and publisher/broadcaster deals. Not necessarily downloadable; measured via metadata the rights-holder publishes. This is where trust success shows up. It will be nearly empty at baseline — that's the point: an empty tier that fills over time is the cleanest evidence of trust impact. Frame it that way preemptively.

Include separate tab on website that outlines what it means to be trust viable, terms of trust, how someone can join, what you get out it

- Tier C — Web-available: Common Crawl–derived volume (FineWeb-2, MADLAD-400). What exists, not what's licensed.

Never sum licensed tiers (A+B) with Tier C. The A/B/C composition per language is itself a key output.

6. Headline statistic: gate progress per language. Licensed data (A+B) ÷ gate threshold, capped at 100%, per gate and per modality. Continuous — every dataset added moves the number, sub-threshold stock never reads as zero, and every trust deal is visible immediately rather than only when a gate flips. The runway chart above is the canonical visual; English appears on it as a reference marker, not a gate.

7. Non-synthetic only. Exclude machine-translated, model-generated, and TTS-generated corpora. Every dataset gets a provenance field; "unknown provenance" is flagged separately, never silently included.

# Week-by-week plan

## Week 1 — Onboarding and setup

Do:

- Read the starter resources and flag any design decision in this plan you disagree with — don't re-derive them.

- Advise which Ethnologue datasets you need access to, and WB will purchase on your behalf.

- Draft the metadata schema: language (ISO 639-3), country, source, modality, size (tokens/hours), license tier, provenance, synthetic flag, retrieval date, retrieval method.

- Set up the Github repo.

Deliverables: metadata schema · repo · access requests filed.

Use this metadata schema + include the measurement status + unit + normalized token estimate

## Week 2 — Population baseline and language list

Do:

- Extract Ethnologue language × country × L1 speaker counts. Record the source and edition behind every count.

- Confirm WBG's Ethnologue license terms for publishing derived data — this affects index release.

- Build the code crosswalk, starting with the langcodes library, SIL's ISO 639-3 tables, and FineWeb-2's language-script labels; patch the mismatches.

- Apply the scope rules (design decision 2) to fix the curated language list. Membership is sticky — a later downward Ethnologue revision doesn't eject a language.

Deliverables: population table · patched code crosswalk · curated language list.

## Week 3 — Text harvest

Do:

- Tier A: harvest the Hugging Face Hub API (by language tag, license, modality) plus OPUS. Published dataset sizes only — no downloading yet.

- Tier B: record any published licensing-deal volumes; stub the trust-reporting fields (Week 6).

- Tier C: pull Common Crawl's per-crawl language statistics — raw bytes per language, across all crawls.

- Calibrate two multipliers against FineWeb-2 (FineWeb for English; MADLAD-400 as cross-check): (a) raw → usable yield, per language = clean FineWeb-2 volume ÷ cumulative raw Common Crawl bytes over the same multi-crawl window — crawls overlap heavily, so calibrating over the matched window makes deduplication implicit in the ratio; (b) byte → token, per script (~10–15 scripts: tokenize one sample language's subset per script under the fixed tokenizer — an afternoon).

- Tier C tokens = raw bytes × yield × token ratio. Then exact-retokenize only gate-adjacent languages (within ~2× of a gate, where multiplier error could flip a conclusion; likely 15–25 languages, small FineWeb-2 subsets).

Out of scope: open-ended GitHub discovery (anything material surfaces on HF or OPUS).

Note on updates: Tier A refreshes event-driven from the HF API; Tier B from trust reports; Tier C refreshes with every new monthly crawl (new raw bytes × multipliers). Report tail languages as trailing averages over several crawls (CLD2 language ID is noisy there); recalibrate both multipliers whenever a derived dataset re-releases.

Deliverables: text volume table (language × tier) · retrieval scripts · calibrated multiplier tables (yield per language, tokens per script) + exact-checked list, all in the repo.

scripts · script-multiplier table + exact-checked list, all in the repo.

If unclear provenance, flag it as unclear and don’t include it in the final dataset.

- Keep track of it though on the backend and figure out what proportion of the data we are pulling has an unverifiable source

Tokenizer/Fertility Rate:

- Since a lot of methodologies are going to be tested on non-Indo European langugaes, look through methods for FineWeb for English and MADLAB-400 to see how they tokenize

## Week 4 — Audio harvest

Do:

- Transcribed hours: Common Voice (API), OpenSLR, FLEURS, VoxPopuli, Bloom Speech/BibleTTS, HF audio datasets.

- Untranscribed hours: HF audio datasets without transcripts, VoxPopuli's ~400K unlabeled hours, MMS-style collections, plus any trust-reported archives.

- Record category (transcribed/untranscribed), license tier, and provenance for every dataset.

Out of scope: a global survey of broadcaster/parliamentary archives (v0.2).

Deliverables: audio hours table (language × category × tier) · scripts.

## Week 5 — Gates

Do:

- Validate the three provisional gate ranges below against the listed papers and practitioner results (fine-tuning studies, Whisper/XLS-R/MMS, scaling laws).

- Pick one point value per gate for computing progress; the ranges become uncertainty bands. (Point values are a presentation convention, not a scientific claim.)

- Write the methods note, capped at 4 pages: gate values with citations and uncertainty bands; the substitution caveat; the frontier-gate caveat and revision schedule.

| Gate | Text (tokens) | Transcribed audio (hours) |
| --- | --- | --- |
| Simple applications — fine-tune existing multilingual models: classification, basic chat, basic ASR | ~10⁷–10⁸ | ~50–500 |
| Domain-specific — health, agriculture, education assistants; reliable ASR | ~10⁹ | ~10³–10⁴ |
| Frontier-grade — performance comparable to high-resource languages, via cross-lingual transfer | ~10¹⁰–10¹¹ | ~10⁴–10⁵ |

Notes for the methods note:

- The top gate is functional, not "parity with English data": capability parity doesn't require data parity (Finnish and Danish reach near-frontier quality on tens of billions of tokens via transfer), and a gate pegged to English's 10T+ corpus is unreachable by construction and drifts as English grows. English stays on the runway as a reference marker only.

- Audio gates are transcribed-hours only in v1.0; the substitution relationship (e.g., ~50K unlabeled + ~10 labeled hours yielding usable ASR) is a documented caveat, not gate math.

- Transfer efficiency varies by script and typological distance, so the frontier gate is the least settled: fix a value, state the uncertainty, revise only on a documented 2–3 year schedule.

Deliverable: methods note (≤4 pages) with cited gate values and uncertainty bands.

Unlabeled vs. Labeled:

- Collect data first and then make a decision about whether first iteraiton of the index uses labeled vs. Unlabeled

- Assume for now that we are not going to label this

## Worked example: Chichewa (all figures illustrative — replace with measured values)

| Chichewa (nya) | Tier A — open | Tier B — rights-cleared | Tier C — web |
| --- | --- | --- | --- |
| Text (tokens) | ~5M | 0 | ~40M |
| Audio, transcribed (hrs) | ~150 | 0 | excluded by design |
| Audio, untranscribed (hrs) | ~1,200 | 0 | excluded by design |

With the simple text gate at 50M tokens: licensed progress = 5M ÷ 50M = 10%; web = 80%. Domain gate (1B): ~0.5% licensed. Audio simple gate (~300 hrs): licensed ≈ 50%, strengthened by the untranscribed stock via substitution. Nothing reads as zero — existing Tier A stock is visible, just far from the gates. Country roll-up: Malawi ≈ 0.7 (Chichewa's L1 share) × 10% ≈ 7% weighted licensed progress on simple-applications text. If the trust licenses ~200M newspaper tokens and ~2,000 broadcaster hours into Tier B, Chichewa's licensed text jumps to 100% of the simple gate and ~20% of the domain gate in one reporting cycle — and every smaller deal moves the bar visibly too. Continuous, attributable, dated movement is the trust's success metric; the gate-crossing is the press release.

## Week 6 — Index construction and automation

Do:

- Join volumes to gates and population: compute gate progress per language (gate × tier × modality) and the country roll-ups.

- Make the refresh one command: documented scripts re-pulling the HF API and Common Voice and ingesting trust reports, every run versioned (versioned baselines enable pre-/post-trust comparisons).

- Draft the trust reporting schema as a Croissant extension (the MLCommons/HF dataset-metadata standard), adding: license class, provenance, synthetic flag, reporting date. Propose a quarterly reporting cadence for trust governance documents. Malawi/MAREN is the pilot adopter.

Out of scope: scheduled automation (v0.2) — "anyone can re-run it" is the v1.0 bar.

Deliverables: v0.1 dataset · one-command refresh · data dictionary · trust reporting schema v0.1.

## Week 7 — Validation and handoff

Do:

- Sanity-check known cases (Swahili, Amharic, Chichewa vs. Estonian, Hindi).

          - These languages were specifically chosen because they approached WB to build trust or approached because they could really use this data for building ai apps

- Spot-check 10–15 datasets for license and synthetic-content errors, prioritizing the gate-adjacent languages from Week 3.

- Produce the runway chart from real data plus a sortable country roll-up table.

- Write the handoff doc: known gaps, refresh instructions, and the v0.2 backlog — monthly Tier C nowcasting, L1+L2 view, archive survey, scheduled automation, computed audio substitution, world map.

- Prepare the 30-minute presentation.

Out of scope: the world map (stretch goal — choropleths of population-weighted progress mislead at a glance and need geo plumbing).

Deliverables: validated v1.0 · runway chart + country table · handoff brief · presentation.

# Deliverables checklist

| Week | Deliverable |
| --- | --- |
| 1 | Metadata schema · repo · access requests filed |
| 2 | Population table · patched code crosswalk · curated language list |
| 3 | Text volume table + scripts + script-multiplier table (repo) |
| 4 | Audio hours table + scripts |
| 5 | Gate methods note (≤4 pages, cited values + uncertainty) |
| 6 | v0.1 dataset · one-command refresh · data dictionary · trust reporting schema (Croissant-based) v0.1 |
| 7 | Validated v1.0 · runway chart + country table · handoff brief · presentation |

If behind schedule: cut the breadth of the curated set (trust languages + the ~50 largest first; the rest stay in the automated set) — never the licensing tiers, the gates, or provenance checking. Agree this fallback in Week 1 so a slip triggers a known plan, not a redesign.

# Starter resources

Frameworks and prior work

- Joshi et al. (2020), "The State and Fate of Linguistic Diversity and Inclusion in the NLP World" — the standard 0–5 resource taxonomy

- Kreutzer et al. (2022), "Quality at a Glance" — why automatic language-ID counts overstate availability; essential cautionary reading

- Meta, "No Language Left Behind" — data collection methodology for 200 languages

- Hoffmann et al. (2022), Chinchilla scaling laws — basis for token-requirement reasoning

Population

- Ethnologue (SIL) — speaker counts by language and country (confirm WBG license terms)

- Glottolog — open cross-check for language inventories

Text

- FineWeb-2 (HF; ~1,900 language-script pairs, per-language sizes published) and FineWeb (English); MADLAD-400; OSCAR; Glot500

- Common Crawl per-crawl language statistics (commoncrawl.org) — the monthly flow signal

- Hugging Face Hub API (huggingface_hub, datasets) — filter by language, license, size; OPUS; Wikipedia dumps

Audio

- Mozilla Common Voice (per-language validated hours, openly licensed, API)

- OpenSLR catalog; FLEURS; VoxPopuli; Bloom Speech / BibleTTS; ML-SUPERB resources

Tooling

- Fixed tokenizer via transformers (e.g., Gemma tokenizer); GitHub REST API for repo discovery

- ISO 639-3 / BCP-47 crosswalk tables (SIL, IANA registry)

# Annex: target output — example language runway (all figures illustrative)

The chart on page 1 is the core published view; this is its table form. Gate progress = volume ÷ gate, capped at 100%. Illustrative point gates: simple = 50M tokens, domain = 1B, frontier-grade = 100B (finalized in Week 5). The audio runway (transcribed hours) uses the identical structure.

| Language | L1 speakers | Licensed (A+B) | Web (C) | Simple (lic. / web) | Domain (lic. / web) | Frontier (lic. / web) |
| --- | --- | --- | --- | --- | --- | --- |
| English (reference) | 390M | ~300B | ~15T | 100% / 100% | 100% / 100% | 100% / 100% |
| Hindi | 345M | ~800M | ~30B | 100% / 100% | 80% / 100% | 0.8% / 30% |
| Estonian | 1.1M | ~1.5B | ~3B | 100% / 100% | 100% / 100% | 1.5% / 3% |
| Swahili | 25M (L1) | ~200M | ~2B | 100% / 100% | 20% / 100% | 0.2% / 2% |
| Hausa | 58M | ~30M | ~300M | 60% / 100% | 3% / 30% | ~0% / 0.3% |
| Chichewa | 14M | ~5M | ~40M | 10% / 80% | 0.5% / 4% | ~0% / ~0% |
| Yao (trust override) | 3M | ~0.3M | ~2M | 0.6% / 4% | ~0% / ~0% | ~0% / ~0% |

What each row demonstrates. English: the reference marker — even English's licensed stock sits two orders of magnitude below its web corpus, so the licensed gap is universal, reframing the index from a deficiency ranking into a global agenda. Estonian: small language, high gates cleared — national language-technology investment shows up directly in the licensed bar. Hindi and Swahili: the web bar clears gates the licensed bar doesn't — the gap between layers is the trust opportunity made visible. Hausa and Chichewa: real sub-threshold stock displayed honestly, with distance-to-gate numbers a minister can quote. Yao: the trust override keeping a small target language on the chart from day one.

Country roll-ups (secondary view): population-weighted average gate progress per country, plus share of population whose L1 has fully cleared each gate — both derived from this table and Ethnologue weights.

Replace all placeholder values with measured figures (Weeks 3–6) before this table or chart appears in any external material.